## HYPNOSIA
GANTT CHART HYPNOSIA Bachelor Thesis
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[5 empty] | 25 May 2020 |  |  |  |  | 01 June 2020 |  |  |  |  | 08 June 2020 |  |  |  |  | 15 June 2020 |  |  |  |  | 22 June 2020 |  |  |  |  | 29 June 2020 |  |  |  |  | 06 July 2020 |  |  |  |  | 13 July 2020 |  |  |  |  | 20 July 2020 |  |  |  |  | 27 July 2020 |  |  |  |  | 03 August 2020 |  |  |  |  | 10 August 2020
[5 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
Hardware
| Study motors characteristics | 2020-05-25 | 2020-05-28 | 4 | bar: 25 May 2020 M to 25 May 2020 Th; 01 June 2020 Th to 01 June 2020 F; 15 June 2020 M to 15 June 2020 F; 13 July 2020 M to 13 July 2020 F; 27 July 2020 M to 27 July 2020 T
| Schematic first prototype | 2020-05-27 | 2020-06-04 | 7 | bar: 25 May 2020 W to 25 May 2020 Th; 01 June 2020 Th; 15 June 2020 M to 15 June 2020 F; 13 July 2020 M to 13 July 2020 F; 27 July 2020 M to 27 July 2020 T
| Component ordering for first prototype | 2020-06-04 | 2020-06-09 | 4 | bar: 01 June 2020 Th to 08 June 2020 T; 15 June 2020 M to 15 June 2020 F; 13 July 2020 M to 13 July 2020 F; 27 July 2020 M to 27 July 2020 T
| Routing and manufacturing first prototype | 2020-06-08 | 2020-06-11 | 4 | bar: 08 June 2020 M to 08 June 2020 Th; 15 June 2020 M to 15 June 2020 F; 13 July 2020 M to 13 July 2020 F; 27 July 2020 M to 27 July 2020 T
| Test and validate PCB | 2020-06-15 | 2020-06-17 | 3 | bar: 01 June 2020 Th to 01 June 2020 F; 15 June 2020 M to 15 June 2020 F; 13 July 2020 M to 13 July 2020 F; 27 July 2020 M to 27 July 2020 T
| Schematic second prototype | 2020-06-29 | 2020-07-09 | 9 | bar: 15 June 2020 M to 15 June 2020 F; 29 June 2020 M to 06 July 2020 Th; 13 July 2020 M to 13 July 2020 F; 27 July 2020 M to 27 July 2020 T
| Component ordering for second prototype | 2020-07-09 | 2020-07-17 | 7 | bar: 15 June 2020 M to 15 June 2020 F; 06 July 2020 Th to 13 July 2020 F; 27 July 2020 M to 27 July 2020 T
| Routing and manufacturing (external) second prototype | 2020-07-13 | 2020-07-17 | 5 | bar: 15 June 2020 T to 15 June 2020 F; 13 July 2020 M to 13 July 2020 F; 27 July 2020 M to 27 July 2020 T
| Test and validate PCB | 2020-07-20 | 2020-07-22 | 3 | bar: 15 June 2020 T to 15 June 2020 F; 13 July 2020 M to 20 July 2020 W; 27 July 2020 M to 27 July 2020 T
Software
| Raspberry Pi Zero familiarization | 2020-05-25 | 2020-06-02 | 7 | bar: 25 May 2020 M to 25 May 2020 Th; 01 June 2020 Th to 01 June 2020 F; 15 June 2020 M to 15 June 2020 F; 13 July 2020 M to 13 July 2020 F; 27 July 2020 M to 27 July 2020 T
| I2C communication protocol | 2020-05-27 | 2020-06-11 | 12 | bar: 25 May 2020 W to 25 May 2020 Th; 01 June 2020 Th to 08 June 2020 Th; 15 June 2020 M to 15 June 2020 F; 13 July 2020 M to 13 July 2020 F; 27 July 2020 M to 27 July 2020 T
| Master's code, V1.0 (basical) | 2020-06-01 | 2020-06-23 | 17 | bar: 01 June 2020 Th to 08 June 2020 Th; 15 June 2020 M to 22 June 2020 T; 27 July 2020 M to 27 July 2020 T
| Matser's code, V2.0 (advanced) | 2020-07-06 | 2020-07-24 | 15 | bar: 06 July 2020 M to 27 July 2020 T
| Slave's code, V1.0 (read I2C basical frame) | 2020-06-08 | 2020-06-26 | 15 | bar: 08 June 2020 M to 08 June 2020 Th; 15 June 2020 M to 22 June 2020 F; 27 July 2020 M to 27 July 2020 T
| Slave's code, V2.0 (read I2C advanced frame) | 2020-07-06 | 2020-07-17 | 10 | bar: 06 July 2020 M to 13 July 2020 F; 27 July 2020 M to 27 July 2020 T
| Drive motors code (bi-axes & tri-axes) and test | 2020-06-17 | 2020-06-26 | 8 | bar: 15 June 2020 W to 29 June 2020 F; 13 July 2020 M to 13 July 2020 F; 27 July 2020 M to 27 July 2020 T
| Synchronize hands manualy first prototype | 2020-06-24 | 2020-07-03 | 8 | bar: 22 June 2020 W to 29 June 2020 F; 13 July 2020 M to 13 July 2020 F; 27 July 2020 M to 27 July 2020 T
| Synchronize hands manualy second prototype | 2020-07-06 | 2020-07-10 | 5 | bar: 29 June 2020 M to 13 July 2020 F; 27 July 2020 M to 27 July 2020 T
| Read JSON via UART | 2020-07-20 | 2020-07-24 | 5 | bar: 15 June 2020 W to 15 June 2020 F; 20 July 2020 M to 20 July 2020 F; 10 August 2020 W to 10 August 2020 F
| Bluetooth communication | 2020-07-23 | 2020-08-07 | 12 | bar: 15 June 2020 W to 15 June 2020 F; 20 July 2020 Th to 03 August 2020 F
| Devlop animation 1 (time) | 2020-07-23 | 2020-08-11 | 14 | bar: 15 June 2020 W to 15 June 2020 F; 20 July 2020 Th to 10 August 2020 T
| Devlop animation 2 (visual movement) | 2020-07-23 | 2020-08-11 | 14 | bar: 15 June 2020 W to 15 June 2020 F; 20 July 2020 Th to 10 August 2020 T
Mechanics
| Design box for first prototype | 2020-05-27 | 2020-06-04 | 7 | bar: 25 May 2020 W to 25 May 2020 Th; 01 June 2020 Th to 01 June 2020 F; 13 July 2020 M to 13 July 2020 F; 27 July 2020 M to 27 July 2020 T
| Manufacturing box for first prototype | 2020-06-04 | 2020-06-11 | 6 | bar: 01 June 2020 Th to 08 June 2020 Th; 13 July 2020 M to 13 July 2020 F; 27 July 2020 M to 27 July 2020 T
| Fixing the hands for first prototype | 2020-06-11 | 2020-06-15 | 3 | bar: 08 June 2020 Th; 15 June 2020 M; 13 July 2020 M to 13 July 2020 F; 27 July 2020 M to 27 July 2020 T
| Design box for second prototype | 2020-07-06 | 2020-07-10 | 5 | bar: 15 June 2020 M to 15 June 2020 F; 29 June 2020 M to 06 July 2020 F; 27 July 2020 M to 27 July 2020 T
| Manufacturing box for second prototype | 2020-07-10 | 2020-07-20 | 7 | bar: 15 June 2020 M to 15 June 2020 F; 06 July 2020 F to 20 July 2020 M
| Fixing the hands for second prototype | 2020-07-17 | 2020-07-22 | 4 | bar: 15 June 2020 M to 15 June 2020 F; 13 July 2020 F to 20 July 2020 W
Document
| Rapport | 2020-05-25 | 2020-08-15 | 60
BeX courses
[34 empty] | First prototype | [26 empty] | Second prototype
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | 25 May 2020 M: WEEK 1; 01 June 2020 M: WEEK 2; 08 June 2020 M: WEEK 3; 15 June 2020 M: WEEK 4; 22 June 2020 M: WEEK 5; 29 June 2020 M: WEEK 6; 06 July 2020 M: WEEK 7; 13 July 2020 M: WEEK 8; 20 July 2020 M: WEEK 9; 27 July 2020 M: WEEK 10; 03 August 2020 M: WEEK 11; 10 August 2020 M: WEEK 12
[5 empty] | 25 May 2020 |  |  |  |  | 01 June 2020 |  |  |  |  | 08 June 2020 |  |  |  |  | 15 June 2020 |  |  |  |  | 22 June 2020 |  |  |  |  | 29 June 2020 |  |  |  |  | 06 July 2020 |  |  |  |  | 13 July 2020 |  |  |  |  | 20 July 2020 |  |  |  |  | 27 July 2020 |  |  |  |  | 03 August 2020 |  |  |  |  | 10 August 2020
[5 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
Hardware
Study motors characteristics | bar: 25 May 2020 M to 25 May 2020 T; 01 June 2020 Th to 01 June 2020 F; 15 June 2020 M to 15 June 2020 F; 13 July 2020 M to 13 July 2020 F; 27 July 2020 M to 27 July 2020 T
Schematic first prototype | bar: 25 May 2020 M to 25 May 2020 Th; 01 June 2020 Th to 01 June 2020 F; 15 June 2020 M to 15 June 2020 F; 13 July 2020 M to 13 July 2020 F; 27 July 2020 M to 27 July 2020 T
Component ordering for first prototype | bar: 08 June 2020 M to 08 June 2020 Th; 15 June 2020 M to 15 June 2020 F; 13 July 2020 M to 13 July 2020 F; 27 July 2020 M to 27 July 2020 T
Routing and manufacturing first prototype | bar: 08 June 2020 M to 08 June 2020 Th; 15 June 2020 M to 22 June 2020 W; 13 July 2020 M to 13 July 2020 F; 27 July 2020 M to 27 July 2020 T
Test and validate PCB | bar: 01 June 2020 Th to 01 June 2020 F; 22 June 2020 F to 29 June 2020 F; 13 July 2020 M to 13 July 2020 F; 27 July 2020 M to 27 July 2020 T
Schematic second prototype | bar: 29 June 2020 F to 06 July 2020 M; 27 July 2020 M to 27 July 2020 T
Component ordering for second prototype | bar: 06 July 2020 W to 06 July 2020 F; 27 July 2020 M to 27 July 2020 T
Routing and manufacturing (external) second prototype | bar: 15 June 2020 T to 15 June 2020 F; 06 July 2020 T to 13 July 2020 F; 27 July 2020 M to 27 July 2020 T
Test and validate PCB | bar: 15 June 2020 T to 15 June 2020 F; 20 July 2020 M to 20 July 2020 T; 27 July 2020 M to 27 July 2020 T
Software
Raspberry Pi Zero familiarization | bar: 01 June 2020 Th to 01 June 2020 F; 15 June 2020 M to 15 June 2020 F; 13 July 2020 M to 13 July 2020 F; 27 July 2020 M to 27 July 2020 T
CAN communication protocol | bar: 13 July 2020 M to 13 July 2020 F; 27 July 2020 M to 27 July 2020 T
Master's code, V1.0 (basical) | bar: 08 June 2020 M to 08 June 2020 Th; 15 June 2020 M to 15 June 2020 Th; 27 July 2020 M to 27 July 2020 T
Matser's code, V2.0 (advanced) | bar: 06 July 2020 W to 13 July 2020 Th; 27 July 2020 M to 27 July 2020 T
Slave's code, V1.0 (read I2C basical frame) | bar: 15 June 2020 Th to 22 June 2020 W; 27 July 2020 M to 27 July 2020 T
Slave's code, V2.0 (read I2C advanced frame) | bar: 06 July 2020 W to 13 July 2020 Th; 27 July 2020 M to 27 July 2020 T; 03 August 2020 M to 10 August 2020 F
Drive motors code (bi-axes & tri-axes) and test | bar: 29 June 2020 W to 29 June 2020 F; 27 July 2020 M to 27 July 2020 T
Synchronize hands manualy first prototype | bar: 06 July 2020 M to 27 July 2020 T
Synchronize hands manualy second prototype | bar: 13 July 2020 M to 13 July 2020 F; 27 July 2020 M to 27 July 2020 T
Read JSON via UART | bar: 15 June 2020 W to 15 June 2020 F; 20 July 2020 W to 27 July 2020 M; 10 August 2020 W to 10 August 2020 F
Bluetooth communication | bar: 15 June 2020 W to 15 June 2020 F; 13 July 2020 F to 20 July 2020 T
Devlop animation 1 (time) | bar: 15 June 2020 W to 15 June 2020 F; 27 July 2020 M to 27 July 2020 W
Devlop animation 2 (visual movement) | bar: 15 June 2020 W to 15 June 2020 F; 27 July 2020 T to 27 July 2020 Th
Mechanics
Design box for first prototype | bar: 13 July 2020 M to 13 July 2020 F; 27 July 2020 M to 27 July 2020 T
Manufacturing box for first prototype | bar: 13 July 2020 M to 13 July 2020 F; 27 July 2020 M to 27 July 2020 T
Fixing the hands for first prototype | bar: 27 July 2020 M to 27 July 2020 T
Design box for second prototype | bar: 15 June 2020 M to 15 June 2020 F; 06 July 2020 W to 06 July 2020 F; 27 July 2020 M to 27 July 2020 T
Manufacturing box for second prototype | bar: 15 June 2020 M to 15 June 2020 F; 13 July 2020 M to 13 July 2020 T; 03 August 2020 F to 10 August 2020 F
Fixing the hands for second prototype | bar: 15 June 2020 M to 15 June 2020 F; 13 July 2020 F to 27 July 2020 T
Document
| Rapport | 2020-05-25 | 2020-08-15 | 60
BeX courses
Intermediate presentation
Formulas:
DURATION (WORK DAYS) = NETWORKDAYS([START DATE],[END DATE])