## HYPNOSIA
GANTT CHART HYPNOSIA Bachelor Thesis
| TASK NAME | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13
|  | 27 July 2020 |  |  |  |  | 03 August 2020 |  |  |  |  | 10 August 2020 |  |  |  |  | 17 August 2020
|  | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
TODO
Fix problem with XF (stack size too small ?) | bar: 27 July 2020 W to 03 August 2020 M; 10 August 2020 M to 10 August 2020 F
Attach and test all watch pointers | bar: 27 July 2020 F to 03 August 2020 W; 10 August 2020 M to 10 August 2020 F
Attach all PCBs to the box | bar: 27 July 2020 F; 03 August 2020 W
Develop code for automatic calibration | bar: 27 July 2020 F; 03 August 2020 Th; 10 August 2020 M to 10 August 2020 T
Develop all animations (1. Time, 2. Write HES, 3. Watch pointers movment, 4. Watch pointers movment) | bar: 27 July 2020 F; 10 August 2020 M to 10 August 2020 Th
Report --> all the software part (raspberry & STM) | bar: 27 July 2020 F; 03 August 2020 F; 10 August 2020 W to 10 August 2020 F
Report --> formatting + final details | bar: 27 July 2020 F; 10 August 2020 M to 17 August 2020 W
Develop text animation | bar: 27 July 2020 F; 10 August 2020 M to 10 August 2020 F; 17 August 2020 Th to 17 August 2020 F
Raspberry Pi 4 -> Raspberry Pi Zero | bar: 27 July 2020 F; 10 August 2020 M to 10 August 2020 F; 17 August 2020 Th to 17 August 2020 F